#1 Meeting Minutes

Duration: 45 minutes

| Date and Time | 21 October 2016, 12 PM Google Meet (online) |
| --- | --- |
| Present | - Fatih Putranda Lesmana, - Edbert Wisely, - Karell Yusdygo, - Hangyeon Cho, - Glenny Vaneesha, and - Yiming Bian |
| Organiser | Karell Yusdygo |
| Minute Taker | Fatih Putranda Lesmana |
| Next Meeting | 25 October 2026 |

Agenda

- Review the Assessment Task 3 website structure, rubric, and current progress.

- Confirm task allocation and responsibilities for each team member.

- Discuss website consistency, prototype/design progress, appendix requirements, AI evidence, and final review needs.

Action Items

| Action Item | Responsible Person | Due Date |
| --- | --- | --- |
| Create Introduction to Lama Lama Country and Background Research | Yiming Bian | 10 PM 26 October 2026 |
| Problem definition and scope section. As well as the project management section | Glenny Vaneesha | 10 PM 26 October 2026 |
| Complete the design process and decision-making. | Karell Yusdygo | 10 PM 26 October 2026 |
| Finish Proposed Solution (based on design process from Karell) | Hangyeon Cho | 10 PM 26 October 2026 |
| Complete Prototyping and Considerations. | Fatih Putranda Lesmana | 10 PM 26 October 2026 |
| Implementation plan and costings. Anticipated considerations and recommendations. | Edbert Wisely | 10 PM 26 October 2026 |
| Complete a final whole-team review of content, citations, links, and website presentation. | All members | During the next online meeting |

Other items

- The group agreed to use a consistent visual theme and formatting across all website pages.

- Each member agreed to review and revise their own section against the assessment rubric before submission.

- AI-use evidence and Prompt Log materials will be declared and collected for the appendices together with the Group Charter and Meeting Minutes.

#2 Meeting Minutes

Meeting Minutes: 2 hours and 45 minutes

| Date and Time | 25 October 2016, 6 PM Google Meet (online) |
| --- | --- |
| Present | - Fatih Putranda Lesmana, - Edbert Wisely, - Karell Yusdygo, - Hangyeon Cho, - Glenny Vaneesha, and - Yiming Bian |
| Organiser | Edbert Wisely |
| Minute Taker | Glenny Veneesha |
| Next Meeting | 28 October 2026 |

- Agenda

- Analyze each member's report section

- Merge all finalized report sections

- Discuss website interface, structure, and animation

- Collect AI evidence log

| Action Item | Responsible Person | Due Date |
| --- | --- | --- |
| Provide ideas for the website interface and body | Yiming Bian | 12 PM 27 October 2026 |
| Provide ideas for the website body | Glenny Vaneesha | 12 PM 27 October 2026 |
| Analyze and review each member's sections | Karell Yusdygo | 12 PM 27 October 2026 |
| Check citations and references | Hangyeon Cho | 12 PM 27 October 2026 |
| Merge each member’s section into 1 file | Fatih Putranda Lesmana | 12 PM 27 October 2026 |
| Complete the website design | Edbert Wisely | 12 PM 27 October 2026 |
| Perform final review of the final report | All members | During the next online meeting |

#3 Meeting Minutes

Meeting Minutes: 1 hour

| Date and Time | 28 October 2016, 9 AM Google Meet (online) |
| --- | --- |
| Present | - Fatih Putranda Lesmana, - Edbert Wisely, - Karell Yusdygo, - Hangyeon Cho, - Glenny Vaneesha, and - Yiming Bian |
| Organiser | Karell Yusdygo |
| Minute Taker | Fatih Putranda Lesmana |
| Next Meeting | - |

- Agenda

- Review the final structure of the report and website

| Action Item | Responsible Person | Due Date |
| --- | --- | --- |
| Review the report and website. Collect feedback and integrate to report/website. | All members | 8 PM 28 October 2026 |